## Sheet1
S/N | Screen Page | Functions Available | Logic | Status | My Remarks | India Team Remarks | India Team Status
Partner Interface Checklist
| Entering partner mode | 0) Page view | From user to change to partner mode | Incomplete | - Background color to change to dark grey (same color as current partner panel background)(to indicate going to partner platform because partner platform most background is dark grey) - Loading bar to shift up above the words (loading bar example pls ask me through whatsapp) |  | Complete
| Exiting partner mode | 0) Page view | From partner to change to user mode | Incomplete | - Spelling error " Exiting partner mode " - Background color to change to white (to indicate going to user platform because user platform most background is white) - Loading bar to shift up above the words (loading bar example pls ask me through whatsapp) |  | Complete
| Partner Main | 0) Page view 1) Panel 2) "Confirmed" tab (UNscrollable) 3) "Available" tab (scrollable) | 0) Page view 1) Panel 2) For partner to view confirmed jobs (default view if there is confirmed job) 3) For partner to view and select available jobs (sorting of list to be discussed) (default view if there is NO confirmed jobs) | 0) Incomplete 1) Done 2) Incomplete 3) Done | 0) - "Confirmed" and "Available" tabs background to be the same color as current panel background (ref to email example) - "Confirmed" and "Available" reduce font size and change color to white - The blue indication bar that will toogle between "Confirmed" and "Available" need to be thicker but shorter (ref to email example) - In between "Confirmed" and "Available" there should be a short divider in light grey color (ref to email example) - Background of "Confirmed" and "Available" need to be dark grey (ref to email example) 2) Cannot be scrolled as there should be enough space for max 2 jobs (ref to "confirmed " tab logic |  | Complete
| Available tab | 0) Page view 1) Available booking info | 0) - Partners can toogle between "Confirmed" and "Available" - The distance info from your location should change according to the partner's location - Available jobs list to limit to 3km radius from partner location 1) Clicking any booking will bring up "Available" Job Details page | 0) Incomplete 1) Done | 0) - Info in box alignment (ref to email example or ask me if do not understand) - Timing format and alignment to be same as email example - The distance info from location to reduce size - Price shown to increase in size (ref to email example) |  | Complete
| Available "Job info" ( Change to "Booking Details" ) | 0) Page view 1) Available Job Details info (unscrollable) 2) Swipe to accept | 0) For Partners to view basic info and accept jobs 1) Basic info for partners to view and accept job 2) Swiping it will accept job (accepted job will automatically go to "Confirmed" tab. | 0) Incomplete 1) Incomplete 2) Incomplete | 0) - Font size, Color, Time format and alignment (ref to email example - Take note of the alignments and example in the example) - The Swipe bar " >> " and color to be exact as email example - The info background to be dark grey (Dark grey color should be same across partner platform) 1) Current view is scrollable (might be bc of screen size issue as you told me yours is unscrollable)(let me know if you need the screenshot) 2) Testing need to be done with actual test run (currently can accept but job does not move to "Confirmed" |  | Complete
| Confirmed tab | 0) Page view 1) Confirmed booking info | 0) - Partners can toogle between "Confirmed" and "Available" - 0 to 20 jobs (1 job slot only) - 21 and above (2 job slots)(once 1 job is completed, it will free up 1 slot for partner to accept another job) - The distance info from your location should change according to the partner's location 1) Clicking any booking will bring up Confirmed "Job info" page | 0) Incomplete 1) Done | 0) - Info in box alignment (ref to email example or ask me if do not understand) - Timing format and alignment to be same as email example - The distance info from location to reduce size - Price shown to increase in size (ref to email example) |  | Complete
| Confirmed "Job info" ( Change to "Job Details" ) | 0) Page view (unscrollable) 1) More 2) Location button (map launcher) 3) View vehicle tab 4) Chat 5) Notes box 6) Info (view only) 7) Swipe to start | 0) To show overall info and functions of job info 1) To bring up "More" box 2) To launch google map and route to vehicle location 3) To switch map view to vehicle view (if any) for easy regconising of vehicle (option to appear only if there is a vehicle photo) 4) pressing this will go to chat page for partner and user to communicate in real time 5) To appear if there is notes (limit to 2 sentence view - if notes is too long, partner will have to click on the notes to view full message from user (will bring up notes box) 6) static view of info entered by user 7) Swipe to start the job and bring up start job confirmation pop out box. | 0) Incomplete 1) Incomplete 2) Incomplete 3) Incomplete 4) Incomplete 5) Incomplete 6) Incomplete 7) Done | 0) - Font size, Color, Time format, divider line color and alignment (ref to email example - Take note of the alignments and example) - The Swipe bar " >> " and color to be exact as email example - The info background to be dark grey (Dark grey color should be same across partner platform) 1) Ref to " More " 2) - To show only location address (take away the " Location " word (ref to email example) - Map launcher not working (color wrong - ref to email example) 3) Ref to logic <-- 4) Chat launcher not working (color wrong - ref to email example) 5) Ref to logic <-- 6) Time format wrong (ref to email example) |  | Complete
| More | 0) Page view 1) Close " X " tab (top left of box) 2) Notes 3) Chat 4) Cancel Job | Pop up box to come up from bottom | Incomplete | Not done (ref to example email) |  | Complete
| Notes | 0) Page view 1) Close " X " tab (top left of box) | Page to come up from bottom. To show full message of what user has keyed in notes | Incomplete | Not done (ref to example email) Need to do live testing |  | Complete
| Chat | 0) Page view 1) Back " < " tab (top left) 2) chat function | For partner to communicate with user through chat (partner must be able to msg with user in real time) | Incomplete | Not done (ref to example email) Need to do live testing |  | InComplete
| Cancel Job | 0) Page view 1) Close " X " tab (top left of box) | Pressing this will bring up "Reason to cancel? " pop up box | Incomplete | Not done (ref to example email) Need to do live testing |  | Complete
| Reason to cancel? | 0) Page view (pop up box) 1) Close " X " tab (top left of box) 2) Unable to locate vehicle 3) Vehicle is heavily caked in mud | There will be only 2 reasons for now (might include more reasons in future) Pressing any reason will cancel the job and close the Job page and return to partner main page | Incomplete | Ref to email example (current view seems to be the old version) |  | Complete
| Confirmation to start job | 0) Page view (pop up box) 1) CANCEL (left) 2) CONFIRMED (right) | 0) Page view 1) pressing this will close the pop up box (job status wont start) 2) pressing this will close the pop up box (job status will start and page will be started "Job Details" - below) | Incomplete | Ref to email example (position of pop up box) |  | Complete
| Started "Job info" ( Change to "Job Details" ) | Same as Confirmed "Job Details" (only difference is 7) 7) Swipe to end | Same as Confirmed "Job Details" (only difference is 7) 7) Swipe to end the job and bring up end job confirmation pop out box | Same as Confirmed "Job Details" | Same as Confirmed "Job Details" |  | Complete
| End job confirmation | 0) Page view (pop up box) 1) CANCEL (left) 2) CONFIRMED (right) | 0) Page view 1) pressing this will close the pop up box (job status wont end) 2) pressing this will close the pop up box (proceed to "Vehicle Photo Submission" page - below) | Incomplete | Ref to email example (position of pop up box) |  | Complete
| Vehicle photo submission | 0) Page view 1) Back " < " tab (top left) 2) vehicle front n rear view photo upload function | 0) Page view 1) To go back to started "Job Details " 2) For partners to submit 1 front vehicle view with no. plate and 1 rear vehicle view with no. plate (once photo is taken, the photo should appear in the boxes) | 0) Incomplete 1) Incomplete | 0) Ref to email example (take note of words color as well) - Background not correct color (dark grey same across partner platform)(correct color is current partner panel background) 1) Able to link to camera function but photo that was taken dont seem to capture into system and is not showing in the boxes (need to do live testing) |  | InComplete
| Vehicle photo submission " Alert " | 0) Page view (pop up box) 1) Alert message 2) Ok | 0) Page view 1) " Please upload photos to end job " 2) Pressing " Ok " will close the alert message box | 0 - 1) Incomplete 2) Done | 0) " ALERT " increase font size abit 1) To be in 1 line sentence (Sentence words error pls check) |  | Complete
| Panel | 0) Page view 1) Partner Profile 2) Earnings 3) SwipeBox 4) Notifications 5) Support 6) Swipe to exit partner mode | 0) Page view 1) To show name and star rating 2) For partners to assess their earnings 3) For partners to redeem their cleaning products 4) For admin to send message from admin panel 5) For users to view FAQ and send feedback 6 ) For Partners to toogle between user and partner mode | 0) Incomplete 1) Done 2) Done 3) Incomplete 4) Incomplete 5) Done 6) Incomplete | 0) Alignment 3) Change icon (same shape but have more white area) 4) Change icon (ask me for example - example to use for all notifications message as well) 6) Ref to email example (be exactly the same as example) |  | Complete
| Profile | 0) Page view 1) Close " X " tab (top left) 2) Joined since DD MM YYYY (view only) 3) Name (view only) 4) Stars (view only) 5) Email (editable) 6) Phone Number (editable) 7) Bank Account Details (editable) 8) Terms of Service 9) Specialist Code of Conduct | 0) Page view 1) To close and return to partner main 2) FYI only 3) FYI only 4) FYI only 5) FYI (editable) 6) FYI (editable) 7) FYI (editable) 8) For partners to view ToS 9) For partners to view CoC | 0) Incomplete 1) Incomplete 2) Done 3) Done 4) Done 5) Incomplete 6) Incomplete 7) Incomplete 8) Incomplete 9) Incomplete | 0) Ref to email example (not to have the blue area at the top) - All info on this page are uneditable (only for those editable info, partners need to click on the edit icon to edit) 1) Current screen is coming in from left and closes towards right (This screen when pressed, should come up from the bottom and close downwards to return to partner main) 5-7) Change edit icon and reduce size (ask me for example on whatsapp) 8) Unclickable (ToS to be provided later in admin panel) 9) Unclickable (Code of Conduct to be provided later in admin panel) |  | Complete
| 4) Edit "Email" | 0) Page view 1) Back " < " tab (top left) 1) Enter new email 2) Continue | 0) Page view 1) To go back to "Profile" 2) For partners to enter new email (Gmail) 3) The "Continue" bar by default will be grey n unclickable, only when a correct email (Gmail) are keyed in then will turn blue and clickable (pressing this will trigger a Email verification to the new email and able to verify through the new email) | 0) Incomplete 1) Incomplete 2) Incomplete 3) Incomplete | Unclickable - (example not yet provided by me - basically is a page for partners to enter their new email and will trigger a email verification to the new email for them to verify) |  | InComplete
| 5) Edit "Phone number" | 0) Page view 1) Back " < " tab (top left) 2) Enter new contact number 3) Continue | 0) Page view 1) To go back to "Profile" 2) For partner to enter new number (8 numbers) 3) The "Continue" bar by default will be grey n unclickable, only when the correct SG numbers (8 numbers) are keyed in then will turn blue and clickable (pressing this will trigger a SMS verification code to the new number and verification page will appear for partner to enter in the code) | 0) Incomplete 1) Done 2) Done 3) Incomplete | 0) Page view 3) ref to logic <-- |  | InComplete
| Edit Phone number verification | 0) Page view 1) Back " < " tab (top left) 2) Verification code boxes 3) Confirm | 0) Page view 1) To go back to edit " Phone number " 2) For partner to key in the code 3) Pressing this will confirmed the change of phone numbers | 0) Incomplete 1) Incomplete 2) Incomplete 3) Incomplete | No example to test |  | InComplete
| 6) Edit "Bank account details" | 0) Page view 1) Back " < " tab (top left) 2) Select Bank " > " tab 3) Enter Account Number 4) Enter Account Holder's Name 5) 2 agreements boxes for acknowledgment ticks 6) Continue | 0) Page view 1) To go back to " Profile " 2) Pressing it will bring in Bank list for partner to select 3) For editing bank account number (keypad comes up only when pressed) 4) For entering bank account holder name (keypad comes up only when pressed) 5) Acknowlegment 6) pressing it will bring up confirmation page | 0) Incomplete 1) Done 2) Done 3) Incomplete 4) Incomplete 5) Incomplete 6) Incomplete | 0) - By default, keypad should not auto come up (only when pressed then come up) - Should not be scrollable (current page is scrollable) - Alignment of words 2-3) Input bank account details field info can use your idea (The words will go up when pressed - ask me to give u example if cannot remember) 4) Duplicate sentences (ref to email example) 5) Continue button not there (confirmation page example not yet provided - basically is a page to display all keyed bank account info for partner to double check and press confirm to submit |  | Complete
| Edit bank account details select bank | 0) Page view 1) Back " < " tab (top left) 2) Bank list (selectable) | 0) Page view 1) To go back to "Edit Bank Account Details" page 2) List of banks for partner to choose and select (to include function to add more banks in future in admin panel) | 0) Page view 1) Done 2) Incomplete | 0) Page view 2) Input banks in bank list (ref to email example for list) |  | Complete
| Earnings | 0) Page view 1) Close ' X ' tab (top left) 2) Cash Balance (view only) 3) "Daily" tab (default) 4) "Weekly" tab | 0) Page view 1) To close page and return to partner main 2) Amount shown will update as jobs are being completed 3) ref to below 4) ref to below | 0) Page view 1) Incomplete 2) Incomplete 3) Incomplete 4) Incomplete | 0) Take note font size and color - Text size and alignment (overall) - Date format 1) - Wrong icon (change to " X ") - Current screen is coming in from left and closes towards right (This screen when pressed, should come up from the bottom and close downwards to return to partner main) Ref to email example (pls ask if not sure) |  | Complete
| Earnings daily | 0) Page view (scrollable) | 0) To view overall earnings within each day (earnings to update as jobs is being completed | Incomplete | - Text size and alignment (overall) - Date format Ref to email example (pls ask if not sure)
| Earnings daily individual job info receipt (history) | 0) Page view | 0) To view receipt | Incomplete | Unable to click into history Job Details Ref to email example (pls ask if not sure) Take note font size and color
| Earnings daily individual job info cancelled receipt (history) | 0) Page view | 0) To view receipt | Incomplete | Example not yet provided (overall is same as job info receipt but $$$ area will be replaced by " Cancelled by Specialist / User " in red color
| Earnings weekly | 0) Page view (scrollable) | 0) To view overall earnings within each week | Incomplete | - Text size and alignment (overall) - Date format Ref to email example (pls ask if not sure)
| SwipeBox | 0) Page view 1) Close ' X ' tab 2) Washes bar (view) 3) REDEEM 4) " ? " info tab 5) Redemption history (scrollable) | 0) Page view 1) To close and go back to Partner main page 2) - To indicate when will redemption be available (1 job = 1 bar) - 6 jobs = redeem (light up " REDEEM " bar)(default is light grey) 3) - This button will only light up when job bar reached 6 washes - Pressing this will bring up " Redemption " page 4) Pop out box with info 5) - Scrollable only from below the " Redemption History " - pressing on any redemption history will bring up "Redemption history info" page | 0) Incomplete 1) Incomplete 2) Done 3) Incomplete 4) Incomplete 5) Incomplete | 0) The dark grey part to be the same dark grey tone as (partner panel "grey" (the dark grey tone should be same across partner platform) 1) - Wrong icon (change to " X ") - Current screen is coming in from left and closes towards right (This screen when pressed, should come up from the bottom and close downwards to return to partner main) 2) NA 3) (Design wise) Pls refer email example 4) - Color of the button (grey) (ref to email example ) - Info inside box is wrong (ref to email example) 5) - Unable to scroll - Unable to click and enter into redemption history info page |  | InComplete
| Redemption | 0) Page view (unscrollable) 1) Back " < " tab (top left) 2) Delivery time 3) Delivery Address " Postal code " box 4) Delivery Address " Search " 5) Unit Number box (optional) 6) Submit | 0) Page view 1) To go back to "SwipeBox" 2) For partner to select delivery time (time to be editable from admin panel as logistic company might have different delivery time) 3) For partner to key in their postal code (default address can be address when registering as partner / need to enter for 1st time but retain 1st time address but editable for future redemption) 4) Pressing this "search" button will auto search the address and auto populate the address on the line below the postal code function. 5) For partner to key in their unit number (if any) 6) Light grey and unclickable when all info is NOT filled Theme blue (current look) when all info is filled | 0) Incomplete 1) Done 2) Incomplete 3) Incomplete 4) Incomplete 5) Incomplete 6) Incomplete | 0) - Ref to email example (delivery time and delivery address is separate boxes ) - Take note of divider line color as well 2) Unclickable 3) Unclickable 4) Unclickable 5) Unclickable (after "unit number" and before the info box put a " # " ( eg. Unit number # [ xx-xxx ] ) 6) Unclickable
| Redemption history info | 0) Page view (unscrollable) 1) Back " < " tab (top left) | Detailed info for redemption history 1) To go back to "SwipeBox" | Incomplete | No example to test (example not yet provided by me)
| Notification | 0) Page view 1) Close ' X ' tab 2) Notifications (view) 3) Delete all dustbin icon (top right) | 0) Page view 1) When pressed, screen to close downwards and return to default main. 2) For users to see what notifications / messages from admin 3) Icon will only appear when there is 1 or more message, pressing the icon will bring up "Delete all confirmation" to confirm delete all message / notifications | 0) Incomplete 1) Incomplete 2) Incomplete 3) Incomplete | 0) - Alignment of " X " and dustbin icon to align with messages box end to end. - Background to be dark grey (same across partner platform) - Current screen has example but unable to click into each notification message 1) Current screen is coming in from left and closes towards right (This screen when pressed, should come up from the bottom and close downwards to return to partner main) 2) Ref to email example 3) Ref to logic <---- |  | Complete
| Notification message | 0) Page view 1) Back " < " tab (top left) 2) Dustbin icon (top right) | 0) Page view 1) To go back to " Notification " 2) For partners to delete all notifications at once by pressing on this function | Incomplete | No example to test (example not yet provided by me)
| Delete all confirmation | 0) Page view 1) Delete all (right) 2) Cancel (left) | 0) Page view 1 & 2) Pop out box for user to select delete all or cancel | Incomplete | No example to test
| Individual delete | 0) Page view 1) Delete | 0) Page view 1) Slide left on individual notification to show dustbin icon and to click on dustbin icon to delete. Instant delete, No confirmation required | Incomplete | Current screen unable to individually delete
| Support | 0) Page view 1) Close ' X ' tab (top left) 2) Box for input feedback 3) Submit | 0) Page view 1) When pressed, screen to close downwards and return to default main. 2) For users to submit feedback if FAQ does not have the answer to their questions. 3) To submit feedback | Incomplete | 1) Current screen is coming in from left and closes towards right (This screen when pressed, should come up from the bottom and close downwards to return to default main) To be discussed if to implement " Search " or "Categorise" |  | Complete